## Sheet1
Work Remotily Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Create a remote work permit form | younes | 20/2/2025 |  | DONE
Configure secure remote access methods (e.g., VPN) | younes |  |  | Secure access established
Train employees on secure remote work practices | younes | 20/2/2025 | document for how to acsses VPN | DONE
Develop a process for recovering data upon contract termination |  |  |  | Process documented and tested
Review and update the policy annually |  |  |  | Policy updated as needed
3. Acceptable Use Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Define prohibited activities in the policy | younes | 20/2/2025 | Policy template | DONE
Distribute the policy to all employees | younes | 20/2/2026 | Email distribution list | DONE
Monitor system usage for compliance | younes | 23/2/2025 | mange engine SW | DONE
Conduct periodic reviews of the policy | younes | 26/2/2025 | Review checklist | DONE
4. Disposal & Destruction Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Identify assets requiring disposal | younes |  |  | Assets identified
Develop a media sanitization procedure | younes | 27/2/2025 | IT policy | on going
Train staff on proper disposal methods | younes | 27/2/2025 | document of how to dispose data | ongoing
Maintain records of disposal activities | younes |  |  | Records maintained for 2 years
Review and update the policy annually | younes | will be review | still new | Policy updated as needed
Work in Safe Areas Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Visitor Access Log | younes | 20/2/2025 | form to be applied
Access Control | younes | 20/2/2026 | logs to be safed
Information Classification Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Classification Criteria | younes | 27/2/2025 | form to be designed
Access Restrictions | younes | 27/2/2026 | list to be aplied
5. Access Control Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Define user profiles and access rights | younes | 27/2/2025 | Access control matrix | Profiles and rights defined
Implement a user registration process | youes | 27/2/2026 | User registration forms | Process implemented
Remove or modify access rights upon employment changes |  | Ongoing | Employee status updates | Rights adjusted promptly
Document all access-related activities |  | Ongoing | Logging system | Logs maintained accurately
9. Data Retention and Disposal Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Define data retention periods for all types of data | younes | 2025-03-02 | Retention schedule template | in progresses
Archive inactive data securely | younes | 2025-03-02 | Archiving software | in progresses
Destroy data classified as "confidential" in the presence of authorized personnel | younes | 2025-03-02 | Shredders/erasure tools | Data destroyed securely
Maintain records of disposal activities | younes | 2025-03-02 | Record-keeping system | Records maintained for 2 years
Review and update the policy annually | IT Director |  | Review checklist | Policy updated as needed
10. Email Usage Policy
Action | Responsible Person | Deadline | Resources Needed | Success Criteria
Define acceptable email usage guidelines | younes | 27/2/2025 | Policy template | Guidelines documented
Block spam and phishing emails at the gateway | younes | ongoing | Email filtering tools | Emails blocked effectively
Review and update the policy annually | IT Director | ongoing | Review checklist | Policy updated as needed