## Risk Register Log
Al Qarib Risk Register Log Form Code: Al Qarib-ISMSF-06-01 Rev. 01
| Activity/Process/Procedure/Service/Origin | Activity type (routine / non-routine / emergency / devices / software / other) | Risk Description | Risk Clssification | Legal Requirments | Risk Cause | Risk Owner | Risk Impact | Current risk assessment | [5 empty] | Assessment of residual risks - results after taking preventive measures
[9 empty] | The control methods used | Likelhood | Extent of Impact | Risk Scale | Treatment decision (accept - reduce - transfer - avoid) | Suggested precautionary measures | Likelhood | Extent of Impact | Risk Scale | Actions that have been taken
| Activity | routine | Staging backup | Can't take backup from all staging vms phase in local envirnoment |  | High cost for backup software , if we take backup from all vms | IT Team | Imact on develper team if any non backup vm is destroyed , they will need do work from scratch | Now, we determine what is top 10 important vms and backup it | 3 | 3 | 9 | reduce | Increase number of vms that are backup by increase license software of backup | 2 | 2 | 4
| Process | devices | Firewall is standalone | Firewall fortigate device is standalone, no exist another device for active/standby |  | High cost of new firewall device | IT Team | If firewall is destroyed for any reason, all local network will stop | We take backup from OS firewall ,to install it if risk happens | 2 | 2 | 4 | accept | In future try buy another firewall | 1 | 1 | 1
| Process | devices | Physical servers are stanalone | We have 2 physical servers with esxi license, but they are work standalone |  | Numbers of created vms on servers are lot, so can't install Vcntre ,cost of vcntre license | IT Team | Can't apply vcentr features on servers & vms ,also if any server is destroyed for any reason all vms will be lost |  | 3 | 3 | 9 | accept | In future buy new physical server and vcentre license and apply active/active | 1 | 1 | 1
| Activity | routine | DR service on Madar cloud | We have Main site, DR site on madar cloud in two different infrastructue , but RPO is 30 min |  | This is max RPO time that can Madar be serve | IT Team | If occur disaster in main site and go to DR site, we will have 30 min of data loss | Test failover, and try create DR site in local environment special fo database | 2 | 5 | 10 | reduce | Create new site on another cloud like azure/aws and that be serve RPO time decrase than Madar | 1 | 3 | 3
| Activity | routine | Backup service on Madar cloud | We take backup from vms daily every 12 hrs, also can't take immediately backup if I need just snapshot |  | This is Madar backup policy | IT Team | If we need restore backup for any vm will be loss od data changes | Take backup from database on storage in our local environment , but it's hard becaust it depend on IPSEC VPN between our network and Madar network | 2 | 4 | 8 | reduse | Take backup for vms in onther madar time on cloud storage | 2 | 2 | 4
| Service | other | IPSEC VPN | Exist regelation between Egypt & Libya, so we can't access Madar network From any network in Egypt , so we do ipsec vpn between out company network and madar network |  | Regelation Policy | IT Team | If IPSEC VPN is down for any reason , we can't access madar network | We have vm on azure to access Madar network as tempriory solution | 2 | 3 | 6 | accept | Still keep vm azure | 1 | 2 | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[12 empty] | 5 |  |  |  | 1 | 0

## User's Manual
User's Manual
Likelhood
Almost Certain | 5 | Happening 2 or more times per month
Very Likely | 4 | Happening (6-12) once a year | [5 empty] | Risk Mitigation | Likelihood | Consequence | Risk score | Risk score | Mitigation actions done
Likely | 3 | Happening (1-5) times a year
Unlikely | 2 | Happening (1-4) times every five years
Improbable | 1 | Has never happened before and there is no reason to think it is any more likely now
Grade | Description | Customer/client Impact | Financial Impact | Health & Safety | Impact on Reputation | Legal Impact
1 | Negligible | No effect | Very little or none | Very small additional risk | Negligible | No implications
2 | Slight | Some local disturbance to normal business operations | Some | Within acceptable limits | Slight | Small risk of not meeting compliance
3 | Moderate | Can still deliver service with some difficulty | Unwelcome but could be borne | Elevated risk requiring immediate attention | Moderate | In definite danger of operating illegally
4 | High | Business is crippled in key areas | Severe effect on income and/or profit | Significant danger to life | High | Operating illegally in some areas
5 | Very High | Out of business; no service to customers/clients | Crippling: the organization will go out of business | Real or strong potential loss of life | Very High | Severe fines and possible imprisonment of staff
[7 empty] | 2 |  | 2
Risk Score
1 to 3 |  | Very Low
4 to 6 |  | Low
7 to 10 |  | Meduim
11 to15 |  | High | [6 empty] | 1
16to25 |  | Very High | [6 empty] | 1
1
| Insignificant | Minor | Significant | Major | Severe
| 1 | 2 | 3 | 4 | 5
Almost Certain | Low | Medium | High | very High | very High
5 | 5 | 10 | 15 | 20 | 25
Likely | Low | Meduim | High | very High | very High
4 | 4 | 8 | 12 | 16 | 20
Moderate | Very Low | Low | Meduim | High | High
3 | 3 | 6 | 9 | 12 | 15
Unlikely | Very Low | Low | Low | Meduim | Medium
2 | 2 | 4 | 6 | 8 | 10 |  |  |  | 2
Rare | Very Low | Very Low | Very Low | Low | Low |  |  |  | 2
1 | 1 | 2 | 3 | 4 | 5 |  |  |  | 2
2
2
legal requirement | [8 empty] | 1
Level of fulfillment of the legal requirement |  | Score | [6 empty] | 1
There are no legal requirements |  | 1
There are legal requirements |  | 2
There are no legal requirements There are legal requirements There are legal requirements, but they are not enforced |  | 3
# | classification | [7 empty] | 1
1 | strategic
2 | Operational
3 | Emergency
4 | technology and information
5 | environmental
6 | Occupational Health and Safety
7 | Financial
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
2
1
2
Impact
Likelihood

## Categories
Asset Categories
Below are examples of information assets that can be found in the company
(People)
Higher Management
Department Managers
Staff - Experts
other employees
External people visiting the organization
(Applications and databases)
application software (licensed)
freeware; shareware
system software
various tools
databases
(Documentation (in paper or electronic form)
Contracts
Records of correspondence with clients and partners
records
brochures
receipts
Equipment and asset documents
Training documents
internal documents
decisions
Reports
plans
Personnel Documents
(IT, communication and other equipment)
Desktops
laptops
Installation discs
UPS devices
power generators
conditioning
network equipment
power wire
servers
phones
mobile phones
printers
Scanners
cameras
backup tapes
portable storage media
measuring devices
fax machines
Alarm
Cards & Card Readers
(Infrastructure)
offices
archives
Warehouse lockers
lockers
(outsourced services)
electric power supply
Contact links
Maintenance of ICT equipment
information systems maintenance
Postal and courier services
auditors
Consultants
supervisory institutions